## Hand-In 2
Task | Main Responsibility | Priority | Status | Start Date | Due Date | % Complete | Notes
UI Design | Anson | Normal | Not Started | 2015-10-05 | 2015-10-09 | 100%
Storyboard | Anson | Normal | Not Started | 2015-10-05 | 2015-10-09 | 100%
UI/SB on Wiki | Anson | Normal | Not Started | 2015-10-05 | 2015-10-09 | 100%
US01.01.01 | Joshua | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US01.02.01 | Joshua | Normal | Not Started |  | 2015-10-09 | 0% | GUI Tests/Cont do
US01.03.01 | Joshua | Normal | Not Started |  | 2015-10-09 | 0% | GUI Tests/Cont do
US01.04.01 | Joshua | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US01.05.01 | Joshua | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US01.06.01 | Joshua | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US01.07.01 | Joshua | Normal | Not Started |  | 2015-10-09 | 0% | GUI Tests/Cont do
US02.01.01 | Salim | Normal | Complete | 2015-10-08 | 2015-10-09 | 100% | I uploaded to github
US02.02.01 | Salim | Normal | Complete | 2015-10-08 | 2015-10-09 | 100% | I uploaded to github
US02.03.01 | Salim | Normal | Complete | 2015-10-08 | 2015-10-09 | 100% | I uploaded to github
US02.04.01 | Salim | Normal | Complete | 2015-10-08 | 2015-10-09 | 100% | I uploaded to github
US02.05.01 | Salim | Normal | Complete | 2015-10-08 | 2015-10-09 | 100% | I uploaded to github
US03.01.01 | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US03.01.02 | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US03.01.03 | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US03.02.01 | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US04.01.01 | Aaron | Normal | Not Started |  | 2015-10-09 | 0%
US04.02.01 | Aaron | Normal | Not Started |  | 2015-10-09 | 0%
US04.03.01 | Aaron | Normal | Not Started |  | 2015-10-09 | 0%
US04.04.01 | Aaron | Normal | Not Started |  | 2015-10-09 | 0%
US04.05.01 | Aaron | Normal | Not Started |  | 2015-10-09 | 0%
US04.06.01 | Aaron | Normal | Not Started |  | 2015-10-09 | 0%
US04.07.01 | Aaron | Normal | Not Started |  | 2015-10-09 | 0%
US04.08.01 | Aaron | Normal | Not Started |  | 2015-10-09 | 0%
US04.09.01 | Aaron | Normal | Not Started |  | 2015-10-09 | 0%
US06.01.01 | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US06.02.01 | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US06.03.01 | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US06.04.01 | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
US06.05.01 | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100% | There is a duplicate on eclass, I made this one up
US09.01.01 | Jake | Normal | Complete | 2015-10-07 | 2015-10-09 | 100%
US09.02.01 | Jake | Normal | Complete | 2015-10-07 | 2015-10-09 | 100%
US09.03.01 | Jake | Normal | Complete | 2015-10-07 | 2015-10-09 | 100%
US10.01.01 | Joshua | Normal | Complete | 2015-10-08 | 2015-10-09 | 100%
US10.02.01 | Joshua | Normal | Complete | 2015-10-08 | 2015-10-09 | 100%
Release Planning | Group | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
Release On Wiki | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
Glossary | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100% | Also worked on by Josh
License | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
Meeting Minutes Wiki | Elias | Normal | Complete | 2015-10-05 | 2015-10-09 | 100%
301 Project Hand-In part 2
2015

## Milestones
Task | Main Responsibility | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
UML and 1st Milston is complete | Group | High | Not Started |  | 2015-10-19 | 0% | #REF!
2nd Milestone Complete | Group | High | Not Started |  | 2015-10-26 | 0% | #REF!
3rd Milestone Complete | Group | High | Not Started |  | 2015-11-22 | 0% | #REF!
4th Mileston Complete | Group | High | Not Started |  | 2015-11-16 | 0% | #REF!
Polish App | Group | High | Not Started |  | 2015-11-30 | 0% | #REF!
Milstone # | Description
1 | Users can sign in locally, setup their profile, and add cards to inventory
2 | Users can sign into server? (elastisearch) and upload profile information to server as well as cards. Persistent across devices.
3 | Users can add friends and view others' inventory (no trading)
4 | Users can make, accept, decline, and counter offer trades. also view current and past trades
301 Project Milestones
2015

## Sheet2 (hidden)
Group
Anson
Salim
Elias
Aaron
Joshua
Jake